FPT UNIVERSITY

Capstone Project — SEP490 — Group G55

HL-MCK AUTOMATION ANTIDETECT BROWSER

(HL-MCK)

CAPSTONE PROJECT REPORT

Report 2 — Project Management Plan

Project Code: SEP490_G55_HLMCK

Document Code: SEP490_G55_HLMCK_PMP_v1.0

Methodology: Iterative & Incremental Model

— Hanoi, Jan 2026 —

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Cost & Time Estimations	4

1.2 Project Objectives	6

1.3 Project Risks	7

2. Management Approach	8

2.1 Project Processes	8

2.2 Quality Management	10

2.3 Project Training Plan	11

3. Responsibility Assignments	12

4. Project Communications	14

5. Configuration Management	14

5.1 Document Management	14

5.2 Source Code Management	15

5.3 Tools & Infrastructures	16

# I. Record of Changes

| Date | A*/M/D | In Charge | Change Description |
| --- | --- | --- | --- |
| 12/01/2026 | A | LongNP | Initialize Project Management Plan (v0.9 draft) |
| 18/01/2026 | M | LongNP | Update Cost & Time Estimations table — 6 stages, 386 pds |
| 25/01/2026 | M | ChucNTM | Add Project Objectives metrics table |
| 01/02/2026 | M | LongNP | Add Project Risks register (5 risks) |
| 02/02/2026 | M | LongNP | Switch methodology section to Iterative & Incremental Model |
| 08/02/2026 | M | ChucNTM | Add Quality Management subsection (objectives, QA approaches) |
| 15/02/2026 | M | ManhPT | Add Project Training Plan + Responsibility Assignments (RACI) |
| 22/02/2026 | M | LongNP | Add Configuration Management (Document + Source Code + Tools) |
| 01/03/2026 | M | LongNP | Issue PMP v1.0 — frozen for Stage 4 Implementation |
| 15/04/2026 | M | LongNP | Update actuals on Project Objectives metrics; add lessons learned |

*A — Added,  M — Modified,  D — Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Cost & Time Estimations

| # | Work Package | Est. Effort (pds) | Deadline |
| --- | --- | --- | --- |
| 1 | Stage 1: Project Initiating (week 1) | 12 |  |
| 1.1 | Prepare for project (kick-off, roles, repo, communication) | 5 | Week 1 |
| 1.2 | Define the project scope & competitor research | 3 | Week 1 |
| 1.3 | Report 1 (Project Introduction) | 4 | Week 1 |
| 2 | Stage 2: Project Planning & Initial Requirements (weeks 2-3) | 32 |  |
| 2.1 | Project planning + 15-week schedule + Vision document | 5 | Week 2 |
| 2.2 | Report 2: Project Management Plan v0.9 | 7 | Week 3 |
| 2.3 | Report 3: SRS v0.9 (Overall Requirements + UC_01-UC_15) | 20 | Week 3 |
| 3 | Stage 3: Software Design (weeks 4-5) | 35 |  |
| 3.1 | Report 2: Project Management Plan v1.0 | 3 | Week 4 |
| 3.2 | Report 3: SRS v1.0 (Functional + Non-functional) | 10 | Week 4 |
| 3.3 | Database Design (SQLite + drizzle migrations) | 2 | Week 4 |
| 3.4 | Report 4: SDS v0.9 (High-Level Design Specifications) | 20 | Week 4 |
| 4 | Stage 4: Implementation (weeks 5-11) — 3 Iterations | 220 |  |
| 4.1 | Implementation Iteration 1 (weeks 5-6) — Auth / License / Profile core / Renderer base | 70 |  |
| 4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.0 | 7 | Week 5 |
| 4.1.2 | Code Package & Unit Testing Report | 10 | Week 5 |
| 4.1.3 | Report 5: Unit Test | 15 | Week 5 |
| 4.1.4 | Report 5: Integration Test | 15 | Week 6 |
| 4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 3 | Week 6 |
| 4.1.6 | Software Package Version 1 (Auth + License + Profile core) | 20 | Week 6 |
| 4.2 | Implementation Iteration 2 (weeks 7-8) — Profile UI / Proxy / Cookie | 70 |  |
| 4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 5 | Week 7 |
| 4.2.2 | Code Package & Unit Testing Report | 15 | Week 7 |
| 4.2.3 | Report 5: Unit Test | 10 | Week 7 |
| 4.2.4 | Report 5: Integration Test | 10 | Week 8 |
| 4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 5 | Week 8 |
| 4.2.6 | Software Package Version 2 (+ Proxy + Cookie + Profile UI overhaul) | 25 | Week 8 |
| 4.3 | Implementation Iteration 3 (weeks 10-11) — Fingerprint / Engine / Automation / REST | 80 |  |
| 4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 3 | Week 9 |
| 4.3.2 | Code Package & Unit Testing Report | 20 | Week 9 |
| 4.3.3 | Report 5: Unit Test | 10 | Week 10 |
| 4.3.4 | Report 5: Integration Test | 10 | Week 10 |
| 4.3.5 | Report 5: System Test | 12 | Week 11 |
| 4.3.6 | Software Package Version 3 (+ Fingerprint + Engine + Automation + REST API + Web Admin) | 25 | Week 11 |
| 5 | Stage 5: Verification & Validation (weeks 12-13) | 70 |  |
| 5.1 | Report 5: System Test Report | 15 | Week 12 |
| 5.2 | Report 6: User Guides (Installation Guides, User Manuals) | 15 | Week 12 |
| 5.3 | Acceptance Test and Support | 10 | Week 13 |
| 5.4 | Final Software Package (Documents, Source Codes, Installer) | 30 | Week 13 |
| 6 | Stage 6: Closing (week 14) | 17 |  |
| 6.1 | Report 7: Final Project Report | 7 | Week 14 |
| 6.2 | Capstone Defense — Presentation File + Live Demo | 10 | Week 14 |
|  | Total Estimated Effort (man-days) | 386 |  |

### 1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | 386 | 452 | Estimated effort required for the project. |
| 2 | Review Defects | Defects per KLOC | 7-14 | 12 | Defects found in document & code reviews. Healthy review density. |
| 3 | Unit Test Defects | Defects per 100 test cases | 6-12 | 0 | Unit Test Round 1 reached 100% pass (392/392). Defect rate kept < 15%. |
| 4 | Integration Test Defects | Defects per 100 test cases | 5-9 | 7.4 | 12 defects / 163 IT TCs (Profile 5, Browser Session 4, Fingerprint 3). |
| 5 | System Test Defects | Defects per 100 test cases | 3-6 | 4.3 | 4 defects / 94 ST TCs (Proxy rotation, task cancel race, /tasks/cancel 500, license revoke delay). |
| 6 | Test Coverage | % | ≥ 75% | 98.2% | Statement + branch coverage from Vitest + Jest reports. |
| 7 | Timeliness | % | ≥ 90% | 93% | Total on-time deliverables / Total project deliverables. |
| 8 | Requirement Completeness | % | ≥ 95% | 97% | Failed if ≤ 75%. 1 minor requirement deferred (proxy rotation P3). |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Playwright / Browser updates break fingerprint scripts | High | Medium | Lock dependency versions in package.json. Monitor Playwright release notes before upgrading; use rebrowser-playwright fork for stability. |
| 2 | Memory leaks from concurrent browser instances | High | Low | Enforce forceful process termination on profile stop. Cap concurrent profiles at 5 (Free Plan) / 10 (Pro). Profile screencast + behaviorSimulator for leaks. |
| 3 | Anti-bot detection failures on advanced sites (Cloudflare, DataDome) | High | High | Scope clearly excludes AI-level CAPTCHA bypass. Focus on standard fingerprint trackers (CreepJS, BrowserLeaks, pixelscan, AmIUnique). Provide opt-in safe-mode. |
| 4 | Schedule overrun on complex fingerprint R&D tasks | Medium | High | Allocate dedicated buffer time in January for Playwright research. Prioritize core engine (Iteration 1) before UI polish (Iteration 2). |
| 5 | Camoufox binary compatibility issues on Windows | Medium | Low | Pre-test Camoufox installation on target OS during Iteration 1. Provide fallback to Playwright + Chromium engine. |
| 6 | Web Admin .env / API key accidentally committed | High | Low | Add .env to .gitignore from day 1; provide .env.example. Rotate keys + audit history if leak detected. |
| 7 | Free-plan vs Pro-plan license logic confusion | Medium | Medium | tweetnacl Ed25519 signature + machine-ID binding. Offline grace 7 days. Polling every 30s on app boot. |
| 8 | PayOS integration delay (sandbox approval) | Medium | Medium | Start PayOS sandbox setup early in Iteration 3. Provide free-plan fallback if PayOS not approved by Stage 5. |

## 2. Management Approach

The team adopts the Iterative & Incremental development model with three (3) build iterations, each producing a working Software Package, to accommodate the iterative nature of browser fingerprint research and to deliver functional software incrementally to the supervisor for continuous feedback. The model is supplemented by a V-Model test discipline so that Unit, Integration and System Tests align with Detailed Design, High-Level Design and SRS respectively.

### 2.1 Project Processes

Development Methodology: Iterative & Incremental Model — 4 phases / 3 build iterations.

The 4-phase / 3-iteration plan:

| Phase | Weeks | Goal | Key Deliverables |
| --- | --- | --- | --- |
| Inception | Week 1-4 | Define vision, scope, requirements, architecture & UI mockups. | Vision, SRS v0.9-v1.0, SDS v0.9, mockups. |
| Iteration 1 (Construction) | Week 5-6 | Build Auth + License + Profile core + Renderer base. First runnable build. | SDS v1.0, SRS v1.1, Software Package V1, Unit + Integration test cases. |
| Iteration 2 (Construction) | Week 7-8 | Add Proxy + Cookie + Profile UI overhaul. Second build with end-user flows. | SDS v1.2, SRS v1.2, Software Package V2, Unit + Integration test cases. |
| Iteration 3 (Construction) | Week 9-11 | Add Fingerprint + Engine + Automation + REST API + Web Admin. Feature-complete build. | SDS v1.3, Software Package V3, full Unit + Integration + first System Test. |
| Verification & Validation (Transition) | Week 12-13 | Test Documentation 5.0/5.3, fix carry-over defects, package final installer. | Test Reports, Final Software Package, Report 6 User Guide. |
| Closing | Week 14 | Final report + capstone defense. | Report 7 + presentation. |

Each Iteration follows the same internal cycle:

- Iteration Planning (½ day) — refine backlog, agree on goal, split tasks per member.

- Analysis & Design — update SRS for the slice, write/refine SDS sections, ER + sequence diagrams.

- Implementation — code in personal branches (long, huy, manh, kien, chucntm), Pull Request to main.

- Unit Test — Vitest / Jest, coverage target ≥ 75%.

- Integration Test — Postman + IPC test, regress already-working modules from previous iterations.

- Iteration Demo (1h) — present working Software Package version to supervisor.

- Iteration Retrospective (½h) — Start/Stop/Continue list; carry actions to next iteration.

#### Scope & Requirements Management

- Backlog kept in GitHub Issues + Project board, ordered by priority.

- MoSCoW prioritization (Must / Should / Could / Won't have).

- Change approval: Minor changes (< 2 days effort) — PM approval; Major changes (> 3 days) — full team CCB approval.

- SRS is refined incrementally (v0.9 → v1.0 → v1.1 → v1.2) — each iteration adds detail only for the next slice.

#### Time Management

- Project duration: 14 weeks (05/01/2026 — 26/04/2026 — 1 buffer week).

- Iteration size: ~2 weeks per iteration (3 iterations total in Stage 4).

- Estimation: Planning Poker for user stories; task breakdown in person-days.

- Tracking: GitHub Project board, weekly progress charts in Report 2 — Project Tracking.

- Major milestones: end of Iteration 1 (V1 demo), end of Iteration 2 (V2 demo), end of Iteration 3 (V3 + first System Test), end of Stage 5 (RC build), end of Stage 6 (Defense).

### 2.2 Quality Management

#### Quality Objectives

- Performance: app cold start < 3s; profile creation < 2s; support 10 concurrent profiles.

- Reliability: crash rate < 0.1%; data loss = 0%; uptime ≥ 99.9% during a session.

- Code Quality: Vitest + Jest coverage ≥ 75% on tested modules; duplication < 5%.

- Security: zero Critical/High vulnerabilities; license + JWT signed; sensitive data isolated per profile.

- Antidetect Effectiveness: pass CreepJS + BrowserLeaks + pixelscan + AmIUnique on at least 3 fingerprint surfaces.

#### Quality Assurance Approaches

Defect Prevention

- Coding Standards: Biome (lint + format) enforced across all JavaScript / TypeScript files (both Electron main process and React renderer).

- React Best Practices: functional components, React Hooks, components kept under 200 lines.

- Electron Best Practices: strict main / renderer separation, contextBridge for IPC, context isolation enabled.

- Design Reviews: architecture reviewed before each iteration starts; Tech Lead approval required before merging to main.

Code Review Process

- Create PR → automated Biome check → 1-2 peer reviews → address comments → Tech Lead approval → Merge.

- SLA: Standard PR (24h), Urgent (4h).

Unit & Integration Testing

- Tools: Vitest (main process), Jest (Node services), Postman (REST), Playwright Test (E2E).

- Coverage targets: business logic 80%, utility functions 90%, overall minimum 75%.

- Integration coverage: REST API endpoints, Electron IPC handlers, Playwright + Camoufox engine integration, proxy connectivity, SQLite migrations.

System Testing

- Functional: verify all defined use cases (positive and negative scenarios).

- Performance: memory leak detection when running multiple concurrent profiles.

- Security: API Key authentication, local data isolation, dependency vulnerability scan (npm audit).

- Compatibility: Windows 10/11 (primary), macOS 13+, Ubuntu 22.04.

Regression Testing

- Automated Vitest + Playwright E2E suite covering critical user flows.

- Executed on every PR (smoke tests) and before each release (full suite).

User Acceptance Testing (UAT)

- Duration: Stage 5 (Verification & Validation, weeks 12-13).

- Participants: supervisor, 3-5 beta testers, QA team members.

- Exit Criteria: all use cases executed, no critical bugs remaining, supervisor sign-off obtained.

Bug Tracking

- Severity: Critical (fix < 24h), High (3 days), Medium (1 week), Low (2 weeks).

- Lifecycle: New → Triaged → Assigned → In Progress → Code Review → Testing → Fixed → Closed.

- Tool: GitHub Issues with labeled priority + module.

### 2.3 Project Training Plan

| Training Area | Participants | When, Duration |
| --- | --- | --- |
| Iterative & Incremental Model — workshop | Entire Team | Before Iteration 1, 4 hours |
| Git & GitHub (Basic + Advanced) | All Developers | Week 1, 8 hours |
| React.js Fundamentals + Hooks | Frontend Devs | Week 1-2, 24 hours |
| Electron.js Development (main / preload / renderer) | All Developers | Week 1-2, 24 hours |
| Browser Fingerprinting fundamentals | Engine Team (Huy, Manh) | Week 2, 16 hours |
| Playwright Automation & rebrowser-playwright | Engine Team | Week 3, 16 hours |
| Fastify + OpenAPI / Swagger UI | REST API team (Manh) | Week 3, 8 hours |
| Web Admin (React + Firebase + PayOS) | Web team (Kien) | Week 3-4, 16 hours |
| Security Best Practices (license, JWT, .env hygiene) | All Developers | Week 4, 8 hours |
| Testing (Vitest, Jest, Playwright Test) | All Developers | Week 2-3, 16 hours |

Continuous Learning:

- Weekly tech talks (30 min).

- Monthly brown-bag sessions on antidetect tooling.

- Pair programming (junior with senior on engine modules).

- Internal wiki / Notion documentation updated each iteration.

- Quarterly security training refresher.

## 3. Responsibility Assignments

Team Roles:

- LongNP — Project Leader, Desktop core (Profile launcher, IPC, packaging, refactor).

- ManhPT — Desktop developer (Profile UI, Fingerprint, REST API + Swagger UI).

- HuyPQ — Desktop developer (Engine, Proxy, Application Logs, Camoufox, Audit Log, Bulk Automation).

- ChucNTM — Documentation lead + App UI (Automation actions, SettingsTab, refactor src/main).

- KienNX — Web Showcase / Web Admin (Auth, License Pro, PayOS, JWT).

RACI Chart: R — Responsible,  A — Accountable,  C — Consulted,  I — Informed.

| Work Package | LongNP (Leader) | ManhPT | HuyPQ | ChucNTM | KienNX |
| --- | --- | --- | --- | --- | --- |
| Prepare for project | A | R | R | R | R |
| Define the project scope | A | R | R | R | R |
| Report 1 (Project Introduction) | A | R | R | R | R |
| Project planning + 15-week schedule | A | R | C | R | C |
| Report 2: Project Management Plan v0.9 | A | C | C | R | C |
| Report 3: SRS v0.9 (Overall Requirements) | C | R | R | A | R |
| Report 2: Project Management Plan v1.0 | A | C | C | R | C |
| Report 3: SRS v1.0 | C | R | R | A | R |
| Database Design (SQLite + drizzle) | A | R | C | C | C |
| Report 4: SDS v0.9 (HLD) | A | R | R | R | R |
| I1 — Report 4: SDS v1.0 | A | R | R | R | R |
| I1 — Code Package & Unit Testing Report | A | R | R | R | R |
| I1 — Auth & License (auth.controller, LicenseModal) | A | R | I | I | R |
| I1 — Profile core + Renderer base | A | R | I | R | I |
| I1 — Web Admin scaffold | I | I | I | I | A |
| I1 — Report 5: Unit Test | C | R | R | A | C |
| I1 — Report 5: Integration Test | C | R | C | A | C |
| I1 — Report 3: SRS v1.1 | C | C | C | A | C |
| I1 — Software Package Version 1 | A | R | R | R | R |
| I2 — Report 4: SDS v1.2 | A | R | R | R | R |
| I2 — Code Package & Unit Testing Report | A | R | R | R | R |
| I2 — Profile UI overhaul + Cookie Manager | R | A | C | R | I |
| I2 — Proxy CRUD + ProxyChecker + Rotator | C | C | A | R | I |
| I2 — Refactor src/main structure | R | C | C | A | I |
| I2 — Report 5: Unit Test | C | R | R | A | C |
| I2 — Report 5: Integration Test | C | R | R | A | C |
| I2 — Report 3: SRS v1.2 | C | C | C | A | C |
| I2 — Software Package Version 2 | A | R | R | R | R |
| I3 — Report 4: SDS v1.3 | A | R | R | R | R |
| I3 — Code Package & Unit Testing Report | A | R | R | R | R |
| I3 — Fingerprint module + dark theme | R | A | C | C | I |
| I3 — Engine Install + Camoufox + perf launch | C | C | A | I | I |
| I3 — Automation actions (mouse, perms, headers) | C | C | C | A | I |
| I3 — REST API + Swagger UI | R | A | C | I | I |
| I3 — Web Admin (Auth + License Pro + PayOS) | I | I | I | I | A |
| I3 — Application Logs streaming + Audit | I | I | A | C | I |
| I3 — Refactor profile launching + remove CDP | A | C | C | I | I |
| I3 — Report 5: Unit Test | C | R | R | A | C |
| I3 — Report 5: Integration Test | C | R | R | A | C |
| I3 — Report 5: System Test | R | R | R | A | R |
| I3 — Software Package Version 3 | A | R | R | R | R |
| Report 5: System Test Report | R | R | R | A | R |
| Report 6: User Guides | A | R | R | R | R |
| Acceptance Test and Support | A | R | R | R | R |
| Final Software Package | A | R | R | R | R |
| Report 7: Final Project Report | A | R | R | R | R |
| Capstone Defense — Presentation + Live Demo | A | R | R | R | R |

## 4. Project Communications

Daily Communication & Meetings: a private Discord server is used for daily voice stand-ups (15 min), quick messaging and screen-sharing debugging sessions.

Task Management: a GitHub Project board tracks the status of iteration tasks (To-do, In Progress, Review, Done).

Iteration Ceremonies (weekly): Iteration Planning (Mon 19:00, ½ day), Iteration Demo (Friday end-of-iteration, 1 h), Iteration Retrospective (immediately after demo, ½ h).

Official Reporting: weekly progress reports and formal document submissions to the supervisor are conducted via Email and Google Drive.

Code Communication: technical discussions on code implementation occur within GitHub Pull Request comments.

## 5. Configuration Management

### 5.1 Document Management

Storage Location: all project documents (SRS, SDS, Meeting Minutes, Test Plans, User Manuals) are stored centrally on Google Drive, organized into:

- 01_Planning — project plan, risk register, weekly reports.

- 02_Requirements — SRS (Report 3), use cases, user stories.

- 03_Design — SDS (Report 4), architecture diagrams, UI/UX mockups.

- 04_Testing — Test plans, test cases, UAT reports (Reports 5.0/5.1/5.2/5.3).

Naming Convention: [SEP490_G55_HLMCK]_[DocType]_v[X.Y]_[Date].docx

Example: SEP490_G55_HLMCK_SRS_v1.0_20260201.docx

Version Control Strategy:

- Draft (0.x): used during internal drafting & peer review (e.g., v0.1, v0.2). Circulated within the team only.

- Major (1.0, 2.0): issued upon supervisor approval at key milestones. Once baselined, no modifications without a formal Change Request.

### 5.2 Source Code Management

Version Control System: Git is used for version control across the entire project lifecycle.

Repository Host: source code hosted on GitHub as a private repository (longnguyen231/SEP490_G55_Automation_Antidetect_Browser).

Branching Strategy: per-developer feature branches merging into main via Pull Request.

- main: production-ready code only. Direct commits prohibited.

- long, huy, manh, kien, chucntm: per-developer branches; rebased onto main before each PR.

- feature/*, bugfix/*, hotfix/*: short-lived, used for isolated work outside personal branches when needed.

Commit Message Convention: <type>(<scope>): <subject> — types: feat, fix, refactor, docs, perf, chore.

Examples (real commits from project):

- feat: stream main process logs to Application Logs tab

- refactor(profiles): migrate legacy engine='cdp' to 'playwright' on load

- perf: improve profile launch speed and Firefox fingerprint accuracy

- docs: research complete for milestone v1.0 Live Screen Stabilization

Pull Request Process:

- All code changes must be submitted via Pull Request on GitHub.

- PRs require review and approval from at least 1 other team member before merging into main.

- Biome (lint + format) checks must pass before a PR is eligible for review.

- Direct commits to main are strictly prohibited at all times.

### 5.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology — Desktop App | Electron 33, React 18, Vite 5, Tailwind CSS 3.4, Bootstrap 5, Monaco Editor, Zustand, Zod |
| Technology — Browser Engine | rebrowser-playwright (Playwright fork), playwright-extra, puppeteer-extra-plugin-stealth, Camoufox (alt engine), fingerprint-generator + fingerprint-injector |
| Technology — Backend (in-app) | Fastify 5 + Express 5 (REST API), @fastify/swagger + @fastify/swagger-ui (OpenAPI), ws (WebSocket live preview), node-cron (scheduler) |
| Database | SQLite via better-sqlite3 12.x; ORM: drizzle-orm 0.45 + drizzle-kit 0.31; key-value via electron-store; Web Admin uses Firebase Auth + Firestore |
| Logging & Monitoring | Pino 10 + pino-pretty (structured logs); @sentry/electron for crash reporting; custom Audit Logger |
| Security & License | tweetnacl + tweetnacl-util (Ed25519 license signature); machine-ID binding (services/machineId.js); JWT for REST API; javascript-obfuscator for release build |
| Testing | Vitest 2.1.9 (main process), Jest 30.x (Node services), Postman (REST), Playwright Test (E2E system test) |
| IDE / Editors | Visual Studio Code, JetBrains WebStorm |
| Diagramming | Draw.io, StarUML, Figma (UI mockups) |
| Documentation | Microsoft Word, Google Docs / Sheets / Slides, Notion (internal wiki) |
| Version Control | GitHub (source code), Google Drive (documents) |
| Build & Packaging | electron-builder 26 (NSIS for Windows, DMG for macOS, AppImage for Linux); electron-vite + electronmon (dev hot reload) |
| Deployment | Local Desktop Build (Windows / macOS / Linux); Web Admin deployed on Cloudflare Pages |
| Project Management | GitHub Issues + Project board, Discord, weekly Reports 1-7 |
| Payment (Web Admin) | PayOS (sandbox + production) |