## Meeting Minutes (W1)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-06 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Project kick-off & topic finalization (HL-MCK Antidetect Browser) |  | Long | 20:30 | 10 min
Competitor research presentations (GoLogin, Multilogin, Dolphin Anty, AdsPower, Hidemyacc) |  | All members | 20:40 | 20 min
Define team roles & responsibilities matrix |  | Long | 21:00 | 20 min
Set up GitHub repo + branching strategy + Discord channel |  | Long | 21:20 | 15 min
Discuss tentative tech stack (Electron + React + Playwright) |  | Huy | 21:35 | 20 min
Confirm meeting schedule with Mentor |  | Long | 21:55 | 15 min
Q&A and scheduling next meeting |  | Long | 22:10 | 20 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Topic finalization |  | Each member presented their topic ideas. After analysing market need, technical feasibility and competitor coverage, the team converged on 'HL-MCK Automation Antidetect Browser' — a desktop antidetect browser with built-in automation. Mentor confirmed the topic is appropriate for SEP490 scope.
Competitor research summary |  | Surveyed 6 representative anti-detect browsers. Multilogin and GoLogin lead the market but have high price + cloud dependency. AdsPower is feature-rich but heavyweight. The team identified opportunity for a lightweight, local-first, Electron-based desktop alternative.
Roles & responsibilities |  | LongNP = PM + Desktop core (Profile launcher, IPC, packaging). ManhPT = Profile UI + Fingerprint + REST API. HuyPQ = Engine + Proxy + Automation + Audit. ChucNTM = Documentation + App UI (Automation actions, Settings). KienNX = Web Admin / Showcase.
Repo & communication |  | GitHub private repo: longnguyen231/SEP490_G55_Automation_Antidetect_Browser. Per-member branches + main protected. Discord channel set up. Weekly meeting on Mon 19:00 (internal) and Wed 19:00 (mentor).
4. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
Stakeholder analysis & 4 user personas |  | ChucNTM | 12/01/2026
Vision document v0.1 |  | ChucNTM | 12/01/2026
Knowledge sharing: Electron + Playwright (1h workshop) |  | HuyPQ | 10/01/2026
Confirm slot meeting với mentor (Wed 19:00) |  | LongNP | 08/01/2026
Push initial empty repo + branch policy README |  | LongNP | 10/01/2026
DECISIONS
The team officially selected HL-MCK Automation Antidetect Browser as the SEP490 Capstone topic.
5-member responsibility matrix approved by Mentor.
Tech stack tentatively locked at Electron 33 + React 18 + Vite + Playwright (rebrowser fork) — final confirmation in W3.
6. NEXT STEPS
NEXT STEPS
Submit Vision document v0.1 to Mentor before the next meeting.
Begin SRS v0.9 drafting — functional requirements.
Each member self-study Electron / React / Playwright basics in own time.
WRAP-UP
Mentor approved topic and team composition. Members agreed on weekly mentor meeting at Wed 19:00. KienNX volunteered for Web Admin / Showcase since he has prior React experience. ChucNTM took ownership of Documentation lead role.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-01-13 | Google Meet

## Meeting Minutes (W2)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-13 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review Vision document v0.1 |  | Chuc | 20:30 | 15 min
Review 4 user personas (Affiliate marketer, Agency QA, E-commerce ops, Growth hacker) |  | Chuc | 20:45 | 15 min
Knowledge sharing: Electron main/renderer + IPC + Playwright |  | Huy | 21:00 | 30 min
Survey 18 fingerprint surfaces (UA, locale, TZ, WebGL, Canvas, Audio…) |  | Manh | 21:30 | 15 min
Plan SRS draft + tech stack confirmation |  | Long | 21:45 | 20 min
Q&A with mentor + next meeting |  | Long | 22:05 | 25 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Review Report 2 – Project Scope Definition |  | The team reviewed defined scope boundaries and confirmed the classification of in-scope and out-of-scope features.
Vision document v0.1 review |  | Mentor pointed out the Vision document missed Non-Functional Metrics. ChucNTM took an action to add Performance, Reliability, Antidetect Effectiveness sections.
4 personas approved |  | Personas covered: solo affiliate marketer, agency QA tester, e-commerce operator, growth hacker. Each persona has goals + pains + tasks. Approved as the basis for SRS scenarios.
Knowledge sharing — Electron + Playwright |  | HuyPQ delivered a 30-min walkthrough: Electron architecture (main/renderer/preload), contextBridge for IPC, Playwright CDP vs Firefox protocol, init-script injection for fingerprint. All members successfully built a hello-world Electron + React app at home.
Fingerprint surface survey |  | ManhPT enumerated 18 surfaces: UA, locale, timezone, WebGL vendor/renderer, Canvas, AudioContext, Client Hints, plugins, fonts, screen, DPR, hardwareConcurrency, deviceMemory, mediaDevices, geolocation, and more. Each will be either spoofed in init-script or via Emulation API. | DUE DATE
Submit finalized Report 2 |  | hoàng | 2026-01-20
Revise Context Diagram |  | đức | 2026-01-20
Update Vision v0.1 with non-functional metrics |  | ChucNTM | 18/01/2026
Draft SRS v0.9 — Functional Requirements (UC_01-UC_15) |  | ChucNTM | 25/01/2026
Confirm tech stack: Electron 33 + React 18 + Vite + Fastify + better-sqlite3 + drizzle + rebrowser-playwright + Camoufox optional |  | LongNP | 25/01/2026
Skeleton repo: src/main + src/preload + src/renderer + electron-builder config |  | LongNP | 25/01/2026
DECISIONS
The revised project scope and core system functions were approved.
Vision v0.1 baseline accepted (with NFR addition due 18/01).
4 personas approved as foundation for use case modelling.
Tech stack candidates locked for verification in W3.
NEXT STEPS
Prepare for reports 3.
ChucNTM to circulate updated Vision v0.2 within 2 days.
All members to self-study tech stack chosen.
Next meeting will review SRS v0.9 Functional Requirements draft.
-Hoang completed the overview. -Duc completed the Management Approach section. -Nghia completed Responsibility Assignments. -Minh completed Project Communications. -Quang completed Configuration Management. -Mentor's guidance for report 2: For the function, add a post for the owner. "The mentor clarified the following issues: - The required deposit amount for customers. - Information that restaurant owners must provide for registration. - Requirements for participants to join the tournament."
Productive session. Mentor commended the depth of competitor research from W1. Action: Vision document NFR addition is the only blocker, all other deliverables on track. | LOCATION OF NEXT MEETING
2026-01-21 | google meet
2026-01-20 | FU Hoa Lac Meeting Room

## Meeting Minutes (W3)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-20 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review SRS v0.9 — Functional Requirements (UC_01-UC_15) |  | Chuc | 20:30 | 30 min
Confirm tech stack & dependencies |  | Long | 21:00 | 15 min
Identify 3rd-party services (Firebase Auth, NaCl, PayOS) |  | Kien | 21:15 | 10 min
Use case modelling + ER diagram v0.1 |  | Chuc | 21:25 | 20 min
Discuss free-plan limit policy |  | Long | 21:45 | 15 min
Mentor Q&A + scheduling |  | Long | 22:00 | 30 min
3. DISCUSSION SUMMARY
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
SRS v0.9 review |  | ChucNTM presented 15 use cases: Auth, License, Profile, Proxy, Script, Task, REST API, Web Admin, Logs. Mentor accepted the scope but requested explicit free-plan limit policy.
Tech stack confirmed |  | Electron 33 + React 18 + Vite 5 + Fastify 5 + Express 5 + better-sqlite3 12 + drizzle-orm 0.45 + rebrowser-playwright 1.52 + Camoufox (optional). Locked in package.json. Build via electron-builder for NSIS / DMG / AppImage.
3rd-party services |  | Firebase Auth (Google OAuth + email/password) for Web Admin sign-up; NaCl/tweetnacl Ed25519 for offline license signature; PayOS for License Pro payment; Sentry-electron for crash reporting.
Use case + ER diagram |  | ChucNTM drafted high-level ER with 9 entities: profiles, proxies, scripts, script_modules, tasks, task_logs, settings, licenses, audit_log. Mentor approved as starting point.
4. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
Complete SRS v0.5 (Non-functional + Appendix) |  | ChucNTM | 01/02/2026
ER diagram + class diagram (level 1) |  | ChucNTM | 01/02/2026
UI mockup low-fi in Figma (12 screens) |  | ManhPT | 01/02/2026
Web Admin sub-repo scaffold + sitemap |  | KienNX | 01/02/2026
Free-plan policy decision proposal |  | LongNP | 27/01/2026
Document Business Rules |  | Đức | 2026-01-28
SRS v0.9 functional requirements baseline approved. |  | Hoàng | 2026-01-28
Tech stack frozen — package.json locked.
PayOS chosen as payment gateway (sandbox first).
Revised Context Diagram was approved.
Actor structure in Use Case Diagram was finalized.
Begin Stage 3 Software Design (Week 4).
Each member to study assigned 3rd-party service for their module.
Mentor to review SRS v0.9 offline before next meeting.
NEXT STEPS
Free-plan policy still open. Tentative: 5 profiles for free, no scheduler, 1 concurrent runtime. Decision in next meeting.
Finalize all workflow diagrams.
2026-01-27 | Google Meet
7. MEETING CONCLUSION
WRAP-UP
Mentor say remove all “Search” actions from the Context Diagram, ensuring it only shows data flows crossing the system boundary. Nghia updates to the Customer actor in the Use Case Diagram, including renaming from Student to Customer and removing inheritance from Guest. The team decided that “View Real-time Table Availability” will extend “Book a Table”, and discussed possibly renaming or removing it to avoid redundancy. Minh merge “Search Billiard Club” into “View Club List,” where search and filtering will be treated as internal functions leading to the club detail screen. For the Admin actor, the team agreed that searching should always lead to a list view (e.g., Search User → View User List). choose “Club” instead of “Store” across all diagrams and documents. Minh fix that from View Club List, Admin can extend to Suspend Club, and the terms Reject, Lock, and Suspend will be unified into a single action: Suspend. The team discussed key workflow requirements, including defining detailed information for table booking, the owner club registration process, post approval procedures, and the tournament participation flow. Quang fix that workflow must clearly distinguish between system-automated actions and manual real-world actions performed by staff or administrators.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-01-29 | google meet

## Meeting Minutes (W4)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-01-27 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review SRS v0.5 with non-functional requirements |  | Chuc | 20:30 | 20 min
ER + class diagram (level 1) walkthrough |  | Chuc | 20:50 | 20 min
UI mockup low-fi presentation (12 screens) |  | Manh | 21:10 | 20 min
Free-plan policy decision |  | Long | 21:30 | 15 min
Spike plan: Playwright + CDP fingerprint parity |  | Huy | 21:45 | 15 min
System architecture & sequence diagrams plan |  | Long | 22:00 | 20 min
Mentor wrap-up + next meeting |  | Long | 22:20 | 10 min
Main Flow Revision |  | 1.2.1 Booking Table: - Add a step to update service information to 12.1 1.2.2 Tournament Process - Rename step 3 to Action - Add step 2 or remove step 3 entirely - Step 9 is a diamond-shaped condition box - Step 16 is for staff to submit 1.2.3 Owner Registration - Change step 4 to Check Information - Step 5 should be written as Yes/No - Still need to add a step to update status: Reject before step 5.1
SRS v0.5 NFR sections |  | Performance: launch profile < 4s; Reliability: 10 concurrent profiles; Code Quality coverage ≥ 75%; Security: zero Critical/High vulnerabilities; Antidetect: pass CreepJS/BrowserLeaks/Pixelscan/AmIUnique.
ER + class diagram review |  | 9 entities reviewed; FK constraints clarified. profiles ↔ proxies (N..1), scripts → tasks (1..N), profiles → tasks (1..N), tasks → task_logs (1..N). Mentor approved.
UI mockup low-fi |  | ManhPT showed 12 screens in Figma: Profile list/form, Proxy manager, Cookie manager, Scripts manager, Tasks page, Browser runtimes, Live preview, Settings, License modal, Engine install modal, App logs, Sidebar. Dark + light themes. | DUE DATE
Free-plan policy |  | Decided: 5 profiles for Free Plan, no scheduler, 1 concurrent runtime. Pro Plan unlocks all. Documented in SRS. | 2026-02-03
Dual-engine spike plan |  | HuyPQ will run a 1-week spike (W5) testing Playwright vs CDP fingerprint parity on CreepJS. If CDP doesn't add value, drop it later in Iteration 3. | 2026-02-03
Set up development environment |  | minh | 2026-02-03
System architecture + 5 sequence diagrams |  | LongNP | 08/02/2026
UI mockup hi-fi (Tailwind, dark/light) |  | ManhPT | 08/02/2026
Spike: Playwright + CDP fingerprint parity |  | HuyPQ | 08/02/2026
Init repo + code base scaffold |  | LongNP | 08/02/2026
Web Admin sitemap + landing wireframe |  | KienNX | 08/02/2026
Coding activities will begin after the database schema is finalized.
SRS v0.5 (with NFR) approved for SDS development.
Free-plan limit: 5 profiles, no scheduler, 1 concurrent runtime.
ER + class diagram level 1 baselined.
Finalize database design and environment setup.
Prepare to start implementation in the next phase.
Stage 3 Design (Week 4) → bridge to Stage 4 Implementation Iteration 1 (Week 5).
All members to review assigned mockup for their module.
Begin code base scaffold in W5.
-Mentor's suggestions for ERD revisions: +Correct the relationship between round, match, and tournament. +Refine the one-to-many relationships for better accuracy. +Clarify the relationship between booking_service and invoice_detail. +Add a transaction_history table to store transaction history. +Add a parameter to view the deposit rate. Mentor compares UI Mockups and ERD data for refinements: -Notes on redundant table creation. Quang's main flow revisions: 1.2.1 Booking Table: -Add a step to update service information to 12.1. 1.2.2 Tournament Process: -Rename b3 to action. -Add b2 or remove b3 entirely. -B9 is a diamond-shaped condition box. -B16 is for staff to submit. 1.2.3 Owner Registration: -Rename b4 to check information. -B5 should be written as yes/no.
Strong design week. KienNX raised concern about ngrok/Cloudflare tunnel cost for REST demo — confirmed free tier OK. Risk: dual-engine architecture might bloat — addressed via W5 spike. | LOCATION OF NEXT MEETING
2026-01-21 | google meet
2026-02-03 | FU Hoa Lac Meeting Room

## Meeting Minutes (W5)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-02-03 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Review System architecture + sequence diagrams |  | Long | 20:30 | 15 min
Review UI mockup hi-fi |  | Manh | 20:45 | 15 min
Review Playwright + CDP fingerprint parity spike |  | Huy | 21:00 | 20 min
SRS v1.0 freeze for Sprint 1 backlog |  | Chuc | 21:20 | 10 min
Sprint 1 kickoff — Auth, License, Profile core |  | Long | 21:30 | 20 min
Branch strategy demonstration |  | Long | 21:50 | 10 min
Mentor wrap-up |  | Long | 22:00 | 30 min
Database Design |  | The mentor guided the database design process based on the finalized ERD. The mentor provides tools to draw the database.
System architecture |  | 5-layer architecture: Renderer (React) ¦ Preload (contextBridge) ¦ Main (Controllers/Services/Engine/Storage) ¦ REST (Fastify) ¦ External targets. Approved by Mentor.
UI hi-fi mockup |  | ManhPT presented final hi-fi designs in Tailwind palette with dark and light themes. Approved with minor color adjustments.
Spike result |  | HuyPQ ran spike — both Playwright and CDP engines pass UA/locale/timezone/WebGL on CreepJS. Decision: keep both engines for Iterations 1-2, decide later if CDP can be dropped. | DUE DATE
SRS v1.0 freeze |  | Released to drive Sprint 1 backlog. Iterations 1, 2, 3 have draft scope. | 2026-02-09
Code base init |  | LongNP committed `9fe63ce code base` (08/02). Electron + Vite + React project scaffolded. App boots Hello World on Win/macOS. | 2026-02-09
Set up the package diagram in the code. |  | minh | 2026-02-09
Setup Web Admin sub-repo scaffold + landing skeleton |  | KienNX | 15/02/2026
Initial fixes & per-developer branch policy (long, huy, manh, kien, chucntm) |  | LongNP | 15/02/2026
Begin Profile storage (better-sqlite3 + drizzle migrations 0001) |  | LongNP | 15/02/2026
auth.controller (login/register/forgotPassword/acceptEula) — start |  | ManhPT | 15/02/2026
The database design approach was approved.
Report 4 was conditionally approved pending minor revisions.
System architecture v1.0 baselined.
SRS v1.0 frozen — change requires CCB approval.
Both Playwright + CDP engines kept for Iterations 1-2.
Complete remaining database schema components.
Write migration scripts and test locally.
Sprint 1 starts officially in W6. Each developer works on personal branch.
First PR review session in W6 mentor meeting.
Profile core demo at end of Iteration 1 (W7).
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
Code base in repository. Camoufox engine timeline parked until Iteration 3 if time permits. Risk: better-sqlite3 native build on macOS arm64 — workaround via prebuild-install. | google meet
2026-02-10 | Google Meet

## Meeting Minutes (W6)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-02-10 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Demo: First Web Admin PR (PR#1) |  | Kien | 20:30 | 10 min
Demo: Electron app boots + initial fixes |  | Long | 20:40 | 15 min
Status: Auth controller progress |  | Manh | 20:55 | 15 min
Discuss better-sqlite3 macOS arm64 build issue |  | Long | 21:10 | 15 min
Plan W7 work — Renderer FE skeleton |  | Chuc | 21:25 | 15 min
Mentor feedback + Q&A |  | Long | 21:40 | 50 min
3. DISCUSSION SUMMARY
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Web Admin PR#1 merged (14/02) |  | KienNX submitted first Web Admin PR — landing scaffold + routing. Reviewed and merged into main. Foundation set for License Pro + PayOS later.
Code base fixes |  | LongNP committed 6bfa545 'fix' (10/02) and 22df526 'fix' (14/02) for Electron + Vite config. Reverted unstable branch to keep main clean.
Auth controller progress |  | ManhPT 50% done on auth.controller (Firebase integration). Will continue into W7.
better-sqlite3 native build on macOS arm64 fails in CI |  | Investigated — workaround via prebuild-install. Action item carried forward.
W7 plan |  | ChucNTM will init renderer FE skeleton: Profile/Proxy/Automation tabs. LongNP will wire up IPC + preload contextBridge.
Backend Development & Testing |  | - The team needs to build backend components for other system functionalities. - Unit testing must be conducted during development. - One team member should be responsible for testing. - Minh stated that next week the team will try to convert all UI into frontend code. - Hoàng will assign tasks to team members for next week to ensure progress is on schedule.
Init renderer FE skeleton (chucntm branch): Profile / Proxy / Automation pages |  | ChucNTM | 22/02/2026
Profile management core (CRUD + storage layer) |  | LongNP | 22/02/2026
Web Admin landing v0.1 |  | KienNX | 22/02/2026
Resolve better-sqlite3 macOS arm64 prebuild-install |  | LongNP | 20/02/2026
Design and redesign the frontend interface for a unified display across all screens. |  | Quang | 2026-03-02
Perform testing in reports 5.1, 5.2, and 5.3 using the code. |  | Đức | 2026-03-02
PR#1 Web Admin merged — scaffold done. |  | Hoàng | 2026-03-02
Branch strategy validated: per-developer branches → main via PR.
macOS arm64 build issue blocked but non-blocking for Windows-first delivery.
Transition from UI design phase to development phase.
MongoDB will be used for backend data storage.
Iteration 1 first deliverable (Renderer skeleton + Profile core) demo in W8.
Mentor to review SRS v1.0 final once available.
All PRs require ≥ 1 peer review before merge.
One team member will oversee unit testing activities.
Slow but stable start. Mentor satisfied with branch discipline. KienNX showed initiative on Web Admin scaffold. Plan: accelerate FE in W7-W8.
NEXT STEPS
2026-02-17 | FU Hoa Lac Meeting Room
Convert UI designs into functional frontend code.
Complete core features: login, logout, and table management.
Strengthen security and authorization handling.
Revise and finalize Report 4 diagrams.
7. MEETING CONCLUSION
WRAP-UP
The meeting focused on reviewing the current progress and preparing for the transition to the development phase. The mentor provided direction for implementation priorities, security considerations, and Report 4 improvements. The team clearly identified next tasks and responsibilities to ensure the project continues according to schedule.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING

## Meeting Minutes (W7)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-02-17 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Demo: ChucNTM renderer FE skeleton (5 commits) |  | Chuc | 20:30 | 15 min
Status: Profile / Proxies / Automation pages |  | Chuc | 20:45 | 15 min
Status: Auth controller completion |  | Manh | 21:00 | 10 min
Status: ProfileForm wiring discussion |  | Long | 21:10 | 15 min
Plan W8 — Core renderer UI components |  | Long | 21:25 | 15 min
Mentor Q&A |  | Long | 21:40 | 50 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Progress Report and Feature Presentation |  | Hoang presented the current implementation progress of the system. Several core features have been developed, including: -Customer login interface -Partner (owner) registration function -System staff login interface -Owner registration approval by staff -Owner login and access to the table management interface -Viewing the table list for customers -Viewing club details -Booking tables at a club
ChucNTM 5 commits in W7 |  | Commits 8e8ca1c 'init project', 3dec3a5 'create profile fe', 6af4a1e 'proxies fe', b01b029 'fix proxie + add extension fe', 8655280 'automation fe'. Renderer FE skeleton ready for IPC integration.
Profile / Proxies / Automation FE pages |  | Each page renders mock data. Awaiting IPC handlers for real data flow. ChucNTM demo on dev server (Vite hot reload).
Auth controller — DONE |  | ManhPT confirmed login/register/forgotPassword/acceptEula complete with Vitest unit tests. Firebase Auth integrated.
ProfileForm wiring |  | LongNP plans to wire IPC + preload contextBridge in W8 to connect ChucNTM's FE with main process. | DUE DATE
Edit registration, login, profile |  | Minh | 2026-03-10
Add tables and additional services to the restaurant owner's system. |  | Nghĩa | 2026-03-10
Renderer UI core completion (Profile / Logging / Cookie / App structure) |  | LongNP | 01/03/2026
Wire IPC handlers + preload contextBridge |  | LongNP | 01/03/2026
ProxyManager UI v1 + Proxy CRUD storage |  | LongNP | 01/03/2026
Continue Profile model schema (drizzle) |  | LongNP | 01/03/2026
DECISIONS
The system workflow will prioritize the owner registration → club management → table booking process.
Renderer FE skeleton accepted (visual structure approved).
auth.controller closed — moved to QA for unit test coverage.
ProfileForm wiring scheduled for W8 (LongNP).
NEXT STEPS
Complete development of club-related features.
Code review on ChucNTM's 5 commits before merging into main.
Mentor will review IPC architecture in W8 demo.
Iteration 1 deliverable: Software Package V1 by W8 end.
WRAP-UP
ChucNTM made big leap on FE this week. Manh's auth controller polished. Risk: Profile launch hangs > 4s on first run — investigation continues.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-02-24 | Google Meet

## Meeting Minutes (W8)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-02-24 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Demo: Core renderer UI components (commit 82528ba) |  | Long | 20:30 | 20 min
Status: ipc/handlers + preload contextBridge wiring |  | Long | 20:50 | 10 min
Status: Profile management E2E flow |  | Long | 21:00 | 10 min
Iteration 1 retrospective (Start/Stop/Continue) |  | All | 21:10 | 20 min
Plan Iteration 2 — Proxy / Cookie / Profile UI overhaul |  | Long | 21:30 | 15 min
Mentor wrap-up + Software Package V1 acceptance |  | All | 21:45 | 45 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Progress Report and Code Demonstration |  | Hoang presented: --User registration with OTP verification via email -Customer login and personal profile display -Customer registration as a partner (club owner) -Staff approval process for owner registration -Email notifications for both approval and rejection cases -Role switching from customer to owner -Owner features: -Table management (add tables) -Service management (add services) -Subscription to system membership packages Quang presented: -Customer viewing club list -Table booking functionality -Deposit payment process -Viewing booking history
Core renderer UI components |  | LongNP commit 82528ba (24/02) — 'Implement core renderer UI components for profile management, logging, cookie management, and application structure'. Followed by 331f56f 'fix UI' and 3e613d9 'delete' obsolete files.
Profile E2E flow demo |  | Demo: Create profile via UI → IPC → controllers/profiles.js → storage/profiles (drizzle) → return to UI. End-to-end flow works.
Iteration 1 retrospective |  | Start: PR review session every Mon. Stop: long PRs (split into smaller ones). Continue: per-developer branches + daily Discord standup.
Iteration 2 plan |  | Goal: Proxy CRUD + ProxyChecker (HuyPQ), Profile UI overhaul + Cookie Manager (LongNP/ManhPT), Refactor src/main (ChucNTM). | DUE DATE
Software Package V1 acceptance |  | Mentor accepts V1 demo. Action: improve error toasts in V2. | 2026-03-16
The owner section shows the rejected club - click to display the reason for rejection -> fill in the information again to resubmit. |  | Nghĩa | 2026-03-16
Software Package V1 — formal release tag |  | LongNP | 01/03/2026
Begin Iteration 2 — CRUD Proxy + ProxyManager |  | LongNP | 08/03/2026
Proxy Checker prototype (HuyPQ branch huy) |  | HuyPQ | 08/03/2026
Refactor src/main → {api, controllers, services, engine, storage} |  | ChucNTM | 08/03/2026
Add Sentry-electron for crash reporting |  | LongNP | 08/03/2026
The system will focus on two main flows: table booking and playing process.
Iteration 1 closed — Software Package V1 accepted.
Iteration 2 backlog approved (Proxy + Cookie + Profile UI overhaul).
Sentry-electron added to dependencies — approved by Mentor.
NEXT STEPS
Continue developing core system functionalities.
Iteration 2 sprint kickoff next Monday (W9 internal).
All modules from V1 enter regression test mode.
Mid-term review with Mentor in W10.
WRAP-UP
First Iteration delivered on time. Mentor commented positively on the 4-week ramp from spec to working code. Carry-over: error UX needs improvement.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-03-03 | FU Hoa Lac Meeting Room

## Meeting Minutes (W9)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-03-03 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Mid-term review preparation (slides + demo) |  | Long | 20:30 | 20 min
Documentation update: SRS v1.1, UC, ER |  | Chuc | 20:50 | 15 min
Spike Proxy Checker (local prototype) |  | Huy | 21:05 | 15 min
Web Admin: Pricing page + landing prototype |  | Kien | 21:20 | 10 min
Plan W10 — full Iteration 2 push |  | Long | 21:30 | 15 min
Mentor Q&A |  | Long | 21:45 | 45 min
Progress Report and Feature Updates |  | Hoang presented: -Owners can resubmit club registration if previously rejected -Owners must configure PayOS information before using the system -Additional system features: +Staff can view the table layout +Staff check-in process: if customers are more than 15 minutes late, the booking is canceled and the deposit is forfeited +Removed unnecessary confirmation button in the payment process -Missing features identified: +Adding services for customers during gameplay +Extending playing time +Changing tables during a session Quang reported: -Identified an issue where bookings spanning from one day to the next may lose date information for the following day
System Improvements and Mentor Feedback |  | The mentor provided several key recommendations: -Support multiple images per table -Standardize naming conventions in the database -Add a guideline for owners to set up PayOS, possibly integrated with email instructions -Ensure all necessary documentation is completed and updated
Mid-term review prep |  | Demo will cover: Profile CRUD, Profile launch (Playwright), basic Cookie + Logging UI. Slides drafted by LongNP and ChucNTM.
Documentation update |  | ChucNTM updated UC, ER, sequence diagrams to match real code. SRS v1.1 (Iteration 2 detailed requirements) ~50% drafted.
Proxy Checker prototype |  | HuyPQ has local prototype (HTTP/SOCKS5 health check via fetch + IP echo). Will commit to branch huy in W10. | DUE DATE
Web Admin Pricing + landing |  | KienNX local prototype. Awaiting merge after mid-term review. | 2026-03-10
W10 plan |  | Heavy push: 30+ commits expected. CRUD Proxy (LongNP), Proxy Checker (HuyPQ), ProxyManager UI + refactor (ChucNTM), Web Admin (KienNX), package.json setup (ManhPT). | 2026-03-10
View restaurant details, make reservations. |  | Quang | 2026-03-10
CRUD Proxy storage + UI |  | LongNP | 15/03/2026
Proxy Checker first demo (PR to main) |  | HuyPQ | 15/03/2026
Web Admin UI landing page final + Pricing |  | KienNX | 15/03/2026
Refactor src/main project structure |  | ChucNTM | 15/03/2026
Mid-term review slides + demo recording (backup) |  | LongNP | 13/03/2026
Tournament features will be developed in the next phase
Mid-term review confirmed for next week with Mentor.
Web Admin module to be pulled forward to Iteration 2 (was planned for Iteration 3).
No code commits this week to focus on review prep + setup CI.
Finalize all three main system flows within the current week
Begin development of the tournament flow in the next week
Mid-term review with Mentor in W10 (target 13/03).
Begin Iteration 2 active push — all developers commit daily.
Carry-over from V1 actions (error UX) addressed in W10.
The meeting reviewed ongoing development progress and identified several missing features and system improvements. The mentor provided guidance on system design, data consistency, and documentation requirements. The team agreed to focus on completing the three core system flows and begin preparing for tournament features and comprehensive testing in the next phase.
A planning + review week, no commits but solid prep work. Mentor satisfied with V1 progress — looks forward to V2 push. | LOCATION OF NEXT MEETING
2026-03-10 | Google Meet

## Meeting Minutes (W10)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-03-10 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Mid-term review with Mentor (slides + demo) |  | Long | 20:30 | 30 min
Demo: Proxy CRUD + ProxyManager UI + Proxy Checker |  | Long, Huy, Chuc | 21:00 | 20 min
Demo: Web Admin sync standard design |  | Kien | 21:20 | 10 min
Status: refactor cấu trúc project + Script tab UI v0 |  | Chuc, Long | 21:30 | 10 min
Plan W11 — Profile UI overhaul + fingerprint |  | Manh | 21:40 | 10 min
Mentor feedback on mid-term |  | All | 21:50 | 40 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Progress Report on Development Tasks |  | -The team completed key components of the tournament system, including tournament bracket logic (single and double elimination) and match scheduling. -Ongoing tasks include revenue reporting backend, admin dashboard, unit testing, Report 4 documentation, and UI improvements. -Additional improvements are being made to resolve conflicts between tournament and booking features.
Mid-term review feedback |  | Mentor positive feedback on V1 + V2 progress. Suggested pulling Web Admin to Sprint 2 instead of 3 — already done.
Proxy CRUD + ProxyManager + Proxy Checker (31 commits this week) |  | LongNP 11 commits ('crud for proxy', 'fix edit proxy, name profile', 'fix proxy protocol'). HuyPQ 12 commits ('Proxy Checker Demo', 'Add Proxy', 'Fix check Proxy'). ChucNTM Proxy Management UI + refactor cấu trúc project (commit 3849ec3).
Web Admin sync standard design |  | KienNX 5 commits: 'giao diện web quản trị', 4× 'commit', 'feat: synchronize all pages with standard design and fix security issues'.
Script tab UI v0 |  | LongNP added Script tab UI skeleton with sessionStorage for profile state. Commits 'UI scritp automation', 'sessionStogare', 'fix UI sctrip'.
ManhPT package.json baseline |  | Setup package.json for branch manh — commit 'manh package json'. Ready for Profile UI overhaul push in W11. | DUE DATE
Admin page design |  | Minh | 2026-03-23
Profile UI overhaul + fingerprint detail pop-up |  | ManhPT | 22/03/2026
Proxy Rotator + CRUD PROXY FIX |  | HuyPQ | 22/03/2026
Fix launch profile + bypass C# old API + remove obsolete SDK |  | LongNP | 22/03/2026
Web Admin: PR#8 (kien branch) merge |  | KienNX | 22/03/2026
Address mid-term action items (error UX, Web Admin pull-forward) |  | All | 22/03/2026
DECISIONS
Mid-term review PASSED — Mentor signed off on Iteration 1 + 2 progress.
Some Proxy Add commits got reverted (PR#5 'Add Crud') — re-added in PR#7.
Iteration 2 considered ~80% done.
System features must be justified and aligned with real-world use cases.
6. NEXT STEPS
Iteration 2 wrap-up in W11 + Iteration 3 kickoff.
Start Profile UI overhaul + Fingerprint pop-up immediately.
Mentor will spot-check next week without formal demo.
Finalize all reports and ensure consistency across documentation.
Strongest week yet (31 commits). Mentor highly satisfied. Risk: Profile UI is becoming bottleneck — ManhPT to take ownership in W11.
WRAP-UP
2026-03-17 | FU Hoa Lac Meeting Room

## Meeting Minutes (W11)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-03-17 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Demo: Profile UI overhaul (13 commits ManhPT) |  | Manh | 20:30 | 20 min
Demo: Proxy Rotator + CRUD fix |  | Huy | 20:50 | 15 min
Demo: Fix launch profile + Refactor action |  | Long | 21:05 | 15 min
Status: Web Admin PR#8 merged |  | Kien | 21:20 | 10 min
Discuss issue: 'fingerprint not faked' unless safe-mode |  | Manh, Huy | 21:30 | 15 min
Plan W12 — Automation engine + Dark theme |  | Chuc, Manh | 21:45 | 15 min
Mentor Q&A |  | Long | 22:00 | 30 min
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Profile UI overhaul (ManhPT 13 commits) |  | From 'clear profile UI' (16/03) → 'fix 1/2 giao dien profile' → 'edit UI profile' → 'add new fingerprint attribute' → 'fix detail fingerprint pop up' → 'fake fingerprint thanh cong' → 'edit headless start'. Profile UI looks production quality.
Proxy Rotator + CRUD fix (HuyPQ 8 commits) |  | 'CRUD PROXY FIX', 'Update Rotator' (×2), 'Fix Proxy', PR#10/#11 merged. Proxy module now production-ready.
Fix launch profile + remove C# SDK (LongNP 8 commits) |  | 'fix launch profile', 'fix action', 'delete api C#' (Revert + redo), 'remove obsolete SDK files and documentation'. Cleanup complete.
Issue: fingerprint not faked unless safe-mode |  | ManhPT discovered after enabling 'fake fingerprint' — works only when safe-mode is enabled, but safe-mode disables Cloudflare bypass. HuyPQ to investigate version mismatch in W12.
Web Admin PR#8 |  | KienNX merged PR#8 for design synchronization. | DUE DATE
Design notifications across all roles. |  | Minh | 2026-03-29
Refactor toàn bộ code structure cho readability + maintainability |  | LongNP | 29/03/2026
Add blocked page detector + fingerprint generator modules |  | LongNP | 29/03/2026
Automation actions (mouse click/move/dbl-click) + storage-state + permissions |  | ChucNTM | 29/03/2026
Dark theme + UI revamp toàn ứng dụng |  | ManhPT | 29/03/2026
Investigate version mismatch — fix 'fingerprint not faked' |  | HuyPQ | 29/03/2026
DECISIONS
Iteration 2 effectively closed — Software Package V2 ready in W12.
Iteration 3 kickoff approved — focus: Fingerprint, Engine, Automation, REST API.
Safe-mode toggle decided as opt-in feature with user warning.
6. NEXT STEPS
NEXT STEPS
Iteration 3 sprint kickoff next Monday.
All members shift to Iteration 3 backlog.
Test fingerprint not-faked issue in isolated env.
WRAP-UP
Profile UI overhaul looks great. ManhPT ramping up well. Carry-over: fingerprint version mismatch is a blocker — must fix in W12.
2026-03-24 | Google Meet

## Meeting Minutes (W12)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-03-24 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
Demo: Automation engine actions (ChucNTM 16 commits) |  | Chuc | 20:30 | 30 min
Demo: Dark theme + UI overhaul (ManhPT 14 commits) |  | Manh | 21:00 | 20 min
Demo: Refactor + blocked page detection + fingerprint gen (LongNP 6) |  | Long | 21:20 | 15 min
Status: Restore main UI + Rotator (HuyPQ 3 commits) |  | Huy | 21:35 | 10 min
Plan W13 — Engine Install + REST API + Cloudflare bypass |  | All | 21:45 | 15 min
Mentor Q&A on Iteration 3 mid-point |  | Long | 22:00 | 30 min
3. DISCUSSION SUMMARY
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Automation engine actions (ChucNTM 16 commits) |  | Major delivery: mouse/click/move/dbl-click/up/down/wheel + grant-permissions + clear-permissions + new-page + storage-state + extra-http-headers + geolocation + swagger-ui-express + SettingsTab. Spans 27/03-29/03. ChucNTM became core contributor for automation.
Dark theme + UI overhaul (ManhPT 14 commits) |  | Series 'fix UI profile, proxy', 'script UI', 'update script UI', 'update proxy UI', 'add pop up', 'log', 'complete basic UI' (×2), 'dark theme part 1/2/3 done'. Polished UI ready for Mentor demo.
Refactor + blocked page detector (LongNP 6 commits) |  | 'fix proxies' (Revert + redo), 'Update browser fingerprint and user agent strings to reflect latest versions', 'Enhance profile management and cleanup in Playwright integration', 'feat: add blocked page detection and fingerprint generation modules', 'Refactor code structure for improved readability and maintainability'.
Restore main UI + Rotator (HuyPQ 3 commits) |  | 'Fix Rotator', 'feat: Restore main UI and integrate custom Rotator features', 'Update FrontEnd'.
Perform Integration Testing |  | Đức : Reviewed the progress of integration testing.Several issues related to data flow and process synchronization were identified for further adjustment.
4. ACTION ITEMS
Engine Install (Chromium / Camoufox / Firefox) + Engine Install Final Update |  | HuyPQ | 05/04/2026
Bypass Cloudflare Turnstile + Audio fingerprint + Firefox engine improvements |  | HuyPQ | 05/04/2026
Click / page-info / screenshot / reload / go-back / go-forward / context/geolocation |  | ChucNTM | 05/04/2026
Refactor ScriptsTab + remove CDP engine + run script + machine code |  | LongNP | 05/04/2026
Profile pop-up + auto-run UI + new script UI + machine code |  | ManhPT | 05/04/2026
5. DECISIONS MADE
Iteration 3 mid-point milestone met — automation engine functional.
Dark theme approved for Software Package V3.
CDP engine removal target moved to W13/W15.
UI consistency (icons, layout) must be standardized before final phase
Documentation must use consistent terminology across all reports
Push hard for Engine Install + Cloudflare bypass in W13.
ManhPT to start Profile UI revamp v2 (auto-run, machine code).
Sprint 3 demo + Iteration 3 retrospective in W14.
Complete User Guide (Report 6)
Massive 39-commit week. Mentor very impressed by automation engine breadth. Risk: too many features to test — QA pressure in W13-W14.
Begin drafting Final Project Report (Report 7)
2026-03-31 | FU Hoa Lac Meeting Room
WRAP-UP
The meeting focused on validating system stability through load and security testing, fixing UI issues, and preparing demo materials. The system is now stable, and the team is transitioning toward documentation completion and final reporting.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-04-13 | Meeting Room

## Meeting Minutes (W13)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-03-31 | FU Hoa Lac Meeting Room |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Demo: Engine Install Final + Cloudflare bypass + perf (HuyPQ 22) |  | Huy | 20:30 | 30 min
Demo: Automation extension (ChucNTM 9 commits) |  | Chuc | 21:00 | 15 min
Demo: Refactor profile launching + remove CDP (LongNP 12) |  | Long | 21:15 | 15 min
Demo: Profile UI revamp + auto-run + machine code (ManhPT 16) |  | Manh | 21:30 | 15 min
Demo: Audio fingerprint + bypass Cloudflare (KienNX 5) |  | Kien | 21:45 | 10 min
Plan W14 — REST API + License + UAT prep |  | All | 21:55 | 20 min
Mentor wrap-up |  | Long | 22:15 | 15 min
Standardize Icon System Across UI |  | Minh presented the review of the current icon usage across the system interface. Several inconsistencies in icon styles and meanings were identified between customer, owner, staff, and admin screens.
Engine Install Final + Cloudflare + perf (HuyPQ 22 commits) |  | Major refactor: 'Sync all changes from main to huy', 'Engine Install Final Update', 'Fix Browser Engine' (multiple), 'CloudFlare Test', 'Playwright browser Update', 'Fix Rotate', 'Update Fìirefox', 'perf: improve profile launch speed and Firefox fingerprint accuracy', 'perf: keep only speed improvement changes'. Cold start improved to ~3s.
Automation extension (ChucNTM 9 commits) |  | 'fix automation newpage', 'grant-permissions và clear-permissions', 'context/pages and context/extra-http-headers', 'context/geolocation', 'reload, go-back, go-forward', 'page-info, content, screenshot', 'click, double-click automation' + 2 PR merges.
Refactor profile launching + Remove CDP (LongNP 12 commits) |  | 'refactor: streamline profile launching and enhance IPC handlers', 'Refactor profile management: update WebSocket handling', 'Refactor: Remove CDP engine and related overrides', 'fix State không đồng bộ', 'Refactor ScriptsTab: Remove duplicate script functionality', 'run script'. CDP engine fully removed!
Profile UI revamp + machine code (ManhPT 16 commits) |  | 'create profile UI' (30/03) → 'add machine code' → 'new logo' → 'auto-run UI' → 'edit scripting module' → 'complete profile unit' → 'toggle button fingerprint' → 'proxy button' → 'done new script UI'. Profile module fully polished.
Audio fingerprint + bypass Cloudflare (KienNX 5 commits) |  | 'add: audio fingerprint', 'revert wrong commit', 'important file', 'resolve conflict', 'bypass cloudfare'. Cloudflare bypass works on test sites. | DUE DATE
Complete Report 7 draft |  | Hoàng | 2026-04-19
Application Logs streaming + Task Log + Script Modules + License key + Camoufox + ProxyPicker |  | HuyPQ | 12/04/2026
Swagger UI + REST API CRUD profile/proxy/script + hot reload API + browser API |  | ManhPT | 12/04/2026
Backend ready signal + IPC handler registration module + fix UI proxy |  | LongNP | 12/04/2026
Web Admin: Auth (Google OAuth + email) + landing + license key + license logic + JWT |  | KienNX | 12/04/2026
Begin Unit Test (Report 5.1) authoring |  | ChucNTM | 12/04/2026
All documentation must strictly match the implemented system
CDP engine officially removed — single Playwright path going forward.
Profile launch speed target met (<3s).
Cloudflare bypass approved as opt-in feature with warning.
6. NEXT STEPS
NEXT STEPS
REST API completion is the W14 priority.
Iteration 3 final review + UAT planning in W14.
Software Package V3 RC build target end of W14.
Finalize project tracking data
Highest-velocity week (64 commits). Mentor congratulated team. Risk: code obfuscation increases startup by ~600ms — acceptable trade-off.
WRAP-UP
2026-04-07 | Google Meet
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-04-20 | Meeting Room

## Meeting Minutes (W14)
PROJECT MANAGEMENT MEETING MINUTES
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
2026-04-07 | Google Meet |  | 20:30:00 | 22:30:00
ATTENDEES
NAME |  | ROLE
Phạm Quang Khang |  | Mentor / Lecturer
Nguyễn Phi Long |  | Project Manager / Team Lead — Desktop core
Phan Tiến Mạnh |  | Developer — Profile UI / Fingerprint / REST API
Phạm Quốc Huy |  | Developer — Engine / Proxy / Automation / Audit
Nghiêm Thị Minh Chúc |  | Documentation Lead + Developer (Automation actions, SettingsTab)
Nguyễn Xuân Kiên |  | Developer — Web Admin / Web Showcase
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
Demo: Application Logs + Task Log + Camoufox + ProxyPicker (HuyPQ 28) |  | Huy | 20:30 | 25 min
Demo: REST API + Swagger UI complete (ManhPT 22) |  | Manh | 20:55 | 20 min
Demo: Web Admin Auth + License Pro + Landing (KienNX 6) |  | Kien | 21:15 | 15 min
Demo: Backend ready signal + IPC handler registration (LongNP 8) |  | Long | 21:30 | 10 min
Iteration 3 retrospective |  | All | 21:40 | 20 min
V&V plan — UT + IT + ST + UAT preparation |  | Chuc | 22:00 | 20 min
Mentor Q&A + final 2-week roadmap |  | All | 22:20 | 10 min
Include a detailed discussion of each agenda item. Include key points, decisions, and information shared during the discussion. Include any presentations or visuals shared during the meeting.
Application Logs + Task Log + Camoufox (HuyPQ 28 commits) |  | Massive delivery: 'feat: stream main process logs to Application Logs tab', 'Application Log Update', 'Update API', 'Update Task Log + Script Modules + App Log', 'Update UI for Theme' (multiple), 'Camoufox + Proxy Select', 'Update Camoufox + Proxy Select + Automation Script Update', 'fix: use engine !== cdp instead of engine === playwright', 'Proxy Update', 'Update Automation', 'Update Engine Install'. Camoufox engine integration complete.
REST API + Swagger UI (ManhPT 22 commits) |  | Full Swagger UI implementation. 'open web swag', 'done swagger UI', 'edit swagger UI profile', 'browser API', 'hot reload API CRUD', 'fix profile API body', 'edit create profile API', 'fix resolution launch zoom', 'toggle button profile', 'refine api swag', 'add data web admin'. 29 REST endpoints production-ready.
Web Admin Auth + License Pro (KienNX 6 commits) |  | 'landing page', 'authentication', 'feat: add authentication with Google OAuth and email/password', 'feat: implement license key system', 'important change', 'update license logic'. Web Admin near production.
Backend ready signal + IPC handler registration (LongNP 8) |  | 'fix UI proxy', '.', 'feat: implement IPC handler registration module', 'feat: add backend ready signal and update broadcaster', 'fix: correct spacing in conditional rendering for profile list'. Main process now production-quality.
Iteration 3 retrospective |  | Start: write unit tests during dev (not after). Stop: commits with single-letter messages ('.'). Continue: per-developer branches + Mentor weekly demos.
4. ACTION ITEMS
Bulk Automation + Function Automation + Audit Log + Engine CamouFox fix |  | HuyPQ | 19/04/2026
REST API completion + bypass profile create through API |  | ManhPT | 19/04/2026
Manage multiple profile + Pagination + view profile + Live screen + project config |  | LongNP | 19/04/2026
Web Admin: License Pro + PayOS + JWT + free trial + bug 401 + .env |  | KienNX | 19/04/2026
Authoring Report 5.1, 5.2, 5.3 + Test Documentation (Report 5.0) |  | ChucNTM | 24/04/2026
Complete project handover and archive |  | All Members | 2026-04-27
Iteration 3 closed — Software Package V3 (feature-complete) accepted by Mentor.
Engine variable bug (lost during merge) fixed — no longer a blocker.
Final Capstone Defense scheduled for 25/04/2026.
Priority is given to fixing system issues and improving stability.
Project is ready for final submission and defense
Stage 5 V&V begins immediately. UAT week of 21/04.
Stage 6 Closing — final report + presentation 24-26/04.
Repo tag v1.0.0 + release notes after defense.
6. NEXT STEPS
Mentor accepted Software Package V3 and approved going to V&V phase. Final 2 weeks focus: testing + documentation + defense. KienNX accidentally committed .env — keys rotated, .env.example added. Risk: 4 carry-over IT bugs to fix in W15.
NEXT STEPS
2026-04-14 | FU Hoa Lac Meeting Room
Finalize all materials (slides, demo, reports)
Deliver project presentation to committee
Archive and handover project after submission
7. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
The meeting confirmed that all project deliverables have been completed and approved by the mentor. The team is now focused on preparing for the final defense, including refining the presentation, practicing delivery, and ensuring a smooth demonstration.
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
2026-05-05 | Meeting Room